## Slide 1
PANDORA TS&F · STRATEGIC PARTNER SELECTION 2027 · THE REQUESTED ALTERNATIVE
The Alternative Approach
Run As-Is First, Earn Agentic
"We found the current approach to be a bit ambitious. Can you propose an alternative?"
Same destination. A gentler on-ramp. The fabric is the destination — never a dependency.
In the deep dive we showed the destination, not the road to it — so it read as if we would do it all from day one. This is the road: we run your platforms as they run today, and travel to the agentic destination step by earned step, at your pace, behind gates you control.
Anchored to contract award, 30 October 2026

## Slide 2
01 WHAT WE HEARD — AND WHAT CHANGES
A real alternative, not repackaging
Dimension | July approach | This alternative
Role of the agentic fabric | Delivery mechanism for scope | Continuous-improvement engine behind scope
Scope coupling | 13 of 30 scope rows delivered "via the fabric" | Zero scope rows depend on the fabric
Day-1 change for Pandora teams | New Teams front door, new patterns | None — same tools, same processes
Adoption decision | Program-level | Per scope item, per readiness gate, Pandora-held dial
Governance on day 1 | Agentic governance active | Service governance active; agentic governance dormant until first dial-up
Prerequisites | Assumed ready | Assessed, then built inside Lane 1 — Gate 0 before anything agentic
Benefits curve | Steeper, earlier | Slower start, same destination — the delta shown openly
What does not change: the destination, the SLAs, the assets, the RFP commitments. The July approach remains available as the accelerated option.

## Slide 3
02 THE MODEL
Two lanes, one destination — three gate kinds
Lane 1 · Run & Deliver — active from day one
Transition per the RFP · your tools & SLAs · migration factories · conventional automation · foundations built as a by-product
Lane 2 · Improve & Evolve — the agentic fabric, held ready
Nothing in the estate until Gate 0 + the item gate pass · per-item dial in Pandora's hand · reversible, audited, quarterly-reviewed
Governance base — service governance active day one · agentic governance pre-built, dormant until the first dial-up
Gate 0 · Foundations
One-time · estate-wide
Makes any dial-up possible at all.
Gate 1 · Assist
Per item · lightweight check
L0 → L1 for that item.
Gate 2 · Agentic
Per item · lightweight check
L1 → L2 for that item.
Only Gate 0 asks us to build something — so only Gate 0 gets its own slide (next). Gate 1 & Gate 2 are the short per-item checks above; every gate is Pandora-owned and reversible.

## Slide 4
03 THE SCOPE — WHAT WE ARE TALKING ABOUT
Your scope of work: 30 items, 13 DevOps + 17 Data & Integration
Taken directly from your platform deep-dive scope mapping — nothing added, nothing dropped. We only make the service level of each item something you dial.
DEVOPS PLATFORM · 13 ITEMS
1. PAKS: Kubernetes, self-service namespaces, provisioning 2. Operating model for PAKS & portal 3. ADO → GitHub foundation 4. End-to-end observability 5. DevEx & onboarding through a single IDP 6. Helios → Port.io migration 7. Tool selection decisions 8. OpsGenie → PagerDuty migration 9. DORA & developer-NPS improvement 10. Transition & continuous improvement 11. K8s / DevTools provisioning & support 12. Cost transparency for the DevOps estate 13. Security, AI-platform & code-quality decisions
DATA & INTEGRATION PLATFORM · 17 ITEMS
1. Data-product workspace in under 30 minutes 2. Nexus → Unity Catalog flow 3. Productionize pipelines & dashboards fast 4. Observe & triage data platforms 5. Cost transparency & showback 6. Single governance layer 7. Open data format, centralized storage 8. Engineering standards for integration 9. Kong API portal & discoverability 10. AI-ready infrastructure for agents 11. Flexible ingestion patterns 12. Real-time + relaxed-latency data mart 13. No data loss / lifecycle transparency 14. AI-ready onboarding & availability 15. Data quality on Kafka 16. Decommission BizTalk 17. Synapse / EDW exit

## Slide 5
04 GATE 0 IN DEPTH
The one gate that needs building — four readiness layers that must hold
You just met the three gates; this is the one that needs building — which is why it, and only it, gets a slide of its own. Lane 1 builds all four layers as a by-product of running the service well, so running as-is first is not a delay on the journey — it is its first leg.
GATE 0 · all four layers proven → unlocks Lane 2
1
Governance readiness
Autonomy without an approval model is just risk.
2
Operations: trace & measure
You cannot gate agents on evidence you cannot measure.
3
People & AI-tool fluency
Agents need supervisors before they need autonomy.
4
Infrastructure & security maturity
An agent is only as safe as the estate that contains it.
Your estate, day one — Lane 1 builds all four layers as it runs

## Slide 6
05 RUN AS-IS
Day one: the RFP delivered as written — anchored to the 30 Oct award
Phase I · Support team
Days 0–60 · Nov–Dec 2026
Full support team hired in; on-parallel shadow of current teams; knowledge acquisition and tooling; handling P3–P5. Bi-weekly readiness assessments throughout.
Phase I · Autonomous
Day 60+ · from late Dec 2026
Full on-call rotation live; P1/P2 ownership; monthly on-call quality evaluation against SLA/SLO.
Phase II · Dev team
Days 60–120 · Jan–Feb 2027
Full dev teams hired in; shadow; knowledge handover; feature development and system operation.
Phase II · Autonomous
Day 120+ · from Mar 2027
Proficient in all dev/ops tasks; proactively lifting quality and delivery efficiency; monthly performance review. Cutover on a 50+ parameter readiness assessment, agreed jointly on evidence.
Tooling — Pandora's own table, unchanged: ServiceNow, New Relic, PagerDuty and GitHub (migrations in flight), Terraform, Jira/Confluence, Port.io.
SLAs — The RFP's own numbers: P1 15-minute acknowledgement / 1.5h RTO · 99.99% mission-critical · error budgets per tier.
RACI — The RFP boundary, unchanged: Pandora retains Lead and Senior Engineers, architecture, standards and roadmap; we run day-to-day.
Migrations — Conventional migration factories: ADO→GitHub, OpsGenie→PagerDuty, Backstage→Port.io, and the BizTalk/EDW/Synapse strangler — playbooks, conversion tooling, cutover evidence.
The only AI on day one — Inside our own delivery team (Claude, GitHub Copilot — tools Pandora already approved). It runs on our machines and pipelines, not in your estate, and needs no governance surface on your side.

## Slide 7
06 RUN AS-IS
People · Technology · Operations — as-is first
People — as-is first
• Day-one staffing is conventional roles per the RFP's resource asks — Kafka, Databricks, Kong, Kubernetes, Terraform engineers; DevOps and JS profiles — through the proven talent model: selection panels, buddy onboarding, quarterly talent reviews.
• Enablement targets the RFP's named gaps (Kubernetes, Kafka, DevOps fundamentals) — valuable regardless of any agentic future.
• Agent-supervisor skills, champions and a CoE are introduced only as dials turn.
No Pandora engineer's job changes on day one. Capability grows by invitation.
Technology — as-is first
• Conventional automation first: runbooks, golden paths, IaC, dashboards — the unglamorous 80% of the value.
• Migrations as factories, not agents — wave plans, conversion playbooks, cutover evidence.
• The fabric sits on the shelf, already built and proven — Pandav on a standard container, skills-as-files in Git, zero net-new infrastructure. Keeping the option open costs nothing.
We are not asking you to fund an option. It already exists.
Operations — as-is first
• ITIL discipline on the RFP's SLAs, human on-call, MTTA/MTTD/MTTR measurement from day one.
• Toil falls first through conventional automation; the trace-and-measure foundation (Gate 0, pillar three) is built here.
• Agentic ops, if and when dialled, arrives read-only first, then drafted-RCA, then gated runbooks — each step behind its own gate.
SLAs are never hostage to novelty.

## Slide 8
07 GOVERNANCE
Two layers, one principle — controls arrive before autonomy
Layer 1 · Service governance — ACTIVE DAY 1
active from day one
• Weekly delivery forum (delivery and engineering leads, both sides)
• Monthly Engineering-Manager → vendor-manager performance feedback
• Escalation paths and joint incident/problem management
• Service reviews: reliability, adoption, developer experience, cost, improvement backlog
Layer 2 · Agentic governance — DORMANT UNTIL DIAL-UP
pre-built, dormant until the first dial-up
• Agent registry, intent catalogue and model catalogue — prepared as templates during Lane-1 quarters
• Risk-tiered autonomy model T0–T4 — action rights by risk, reversibility and environment
• Full audit trail design: every request, context package, approval, tool call and output traceable
• Evaluation scorecards and AI FinOps — activated with the first estate touch, never before
The quarterly dial review joins the two layers — every item's level, decided by Pandora. "Not yet" is always valid.

## Slide 9
08 THE TEAM
One team, three locations — not a hand-off
One team · one backlog · one leader · one knowledge base
Copenhagen
Onsite · Pandora HQ
Leadership, liaison and trust — embedded with your leaders
• Sapient Engagement Principal
• Solution / Engineering lead
• Rotating SMEs, 1–2× a year
WHERE ITS EFFORT GOES TODAY
Lane 1 · Run & Deliver 65%
Lane 2 · Improve & Evolve 35%
Bucharest
Nearshore · Romania
Timezone overlap with Copenhagen — senior engineering and fast feedback
• Senior / lead engineers
• QE / SDET
• Delivery coordination
WHERE ITS EFFORT GOES TODAY
Lane 1 · Run & Deliver 80%
Lane 2 · Improve & Evolve 20%
Gurgaon
Offshore · India
Engineering and 24/7 operations scale — the delivery backbone
• Data · Kafka · DevOps · Cloud engineers
• Development + Operations rotation
• AgentOps skill authoring
WHERE ITS EFFORT GOES TODAY
Lane 1 · Run & Deliver 88%
Lane 2 · Improve & Evolve 12%
Read every bar the same way: each location is mostly Lane 1 today. The coral Lane 2 slice is not a second team — it is the same people doing enablement, and it grows only as you turn dials.

## Slide 10
09 THE TEAM
One leader across all tracks — and Pandora on the wheel
Pandora leadership — retains architecture · standards · roadmap · Lead & Senior Engineers
↕ pairs 1:1 — one accountable line
One Sapient Engagement Principal — senior engineering leader; orchestrates through the track SMEs
Draws on — Sapient senior thought leadership & global CoE
Pandora's direct line to every track lead — transparent & encouraged
Data & Integration
Deep SME — Databricks · Kafka · integration
DEV Data · Kafka · Delta · Unity Catalog
OPS Streaming ops · DQ · lineage
DevOps & Cloud
Deep SME — Kubernetes · Terraform · CI/CD
DEV CI/CD · GitHub Actions · Terraform
OPS PAKS/AKS · SRE · 24/7 on-call
AgentOps & Enablement
Deep SME — AI platform · evals · FinOps
DEV Skills authoring · AI tooling
OPS Evaluations · AI FinOps · adoption
WHO DECIDES, WHO DOES — CONTROL BY DESIGN
Direction & roadmap
Architecture
Standards
Gate 0 / 1 / 2 sign-off
Improvement backlog
Day-to-day delivery
Operations & on-call
■ Pandora-owned ■ Joint ■ Sapient-run
No one person is the deep expert in everything: each track carries its own SME, the Principal orchestrates through them and draws on Sapient's senior thought leadership — while every gate needs a named Pandora sign-off.

## Slide 11
10 THE TEAM
Why two teams? One team, sequenced — dev & ops converge
Not two teams — one team, sequenced. The transition stabilises the running service (the support wave) before it takes on change (the dev wave); the destination is a single team that builds and runs. What makes that possible is the agentic dial itself: Level 2/3 operations removes the operational cognitive load that forced development and operations apart, so a build-minded engineer can own what they run without being a full-time ops specialist.
Development
Operations · 24×7
One team
build it · run it · agent-supervised
Agentic ops (Ops L2/L3) removes the operational cognitive load — so build-minded engineers can own what they run.
A layered core, not uniform heroes
An experienced SRE/DevOps backbone holds 24×7 and the hard incidents; development engineers take on-call for what they build, with agentic ops carrying the toil.
Rotation & pairing
Engineers rotate between development and operations, building the build-and-run mindset over the journey rather than hiring for it fully formed.
Follow-the-sun — 24×7 by design
Copenhagen, Bucharest and Gurgaon cover the clock, so no individual carries an unsustainable pager — and dialled agentic ops cuts the night wake-ups further.
Select for mindset, enable the rest
We screen for ownership and curiosity, then close skills through Gate-0 enablement — the same clinics that build capability build the mindset.

## Slide 12
11 THE TEAM
Skills coverage — Ops L1→L3 into Development, and knowledge transfer that sticks
Engineering skill | Ops L1 · Monitor & route | Ops L2 · Diagnose & restore | Ops L3 · Engineer fix | Improve & Evolve · Lane 2 backlog | Development · Build & change
Data engineering | Pipeline alerts, failed-run routing, first checks | Rerun, quarantine, DQ triage, lineage lookup | Spark / Delta fix PR, model and job optimisation | Backlog: auto-DQ triage, self-healing reruns, templates as dial-up candidates | Data-product build, medallion design, reusable templates
Kafka / Confluent | Lag, schema and connector alerts | Replay, rebalance, connector restart, config triage | Connector, schema or consumer fix PR | Backlog: self-healing connectors, schema-drift auto-remediation candidates | Event contracts, producer / consumer engineering
DevOps / CI-CD | Failed-build routing and known-error checks | Runner, secret and pipeline recovery | Workflow / action refactor PR, policy-gate fix | Backlog: flaky-pipeline auto-remediation, policy-as-code dial-up candidates | GitHub migration factory and platform pipeline patterns
Cloud · Kubernetes · Terraform | Pod, node, quota and certificate monitoring | Rollback, scale, config restore and access triage | IaC, Helm or platform fix PR | Backlog: self-heal and auto-scale recipes, drift-correction candidates | PAKS recipes, self-service patterns, platform engineering
SRE / Observability | Alert intake, severity routing, dashboard checks | Correlation, RCA draft, runbook-guided restore | Instrumentation, SLO or reliability fix PR | Backlog: auto-RCA, alert-noise reduction, SLO-guard automation candidates | Observability-by-design and resilience engineering
QE / SDET | Smoke-test results and release-health checks | Regression triage, data-quality failure isolation | Test-harness and quality-gate fix PR | Backlog: self-maintaining tests, failure auto-triage, risk-based selection | Automation strategy, contract tests, CI quality gates
KNOWLEDGE TRANSFER — A DESIGNED LOOP
1. Acquire
On-parallel shadow of current teams; tooling and access
2. Document
Living runbooks, ADRs, architecture and a knowledge wiki
3. Play back
Reverse-shadow — we play knowledge back to your incumbent SMEs
4. Certify
Enablement clinics and certifications against readiness thresholds
5. Own
Pandora can operate any capability we deliver — the acceptance bar
Full coverage day one across dev & ops — incl. the Kubernetes, Kafka & DevOps fundamentals your RFP flagged as thin.

## Slide 13
12 THE TEAM
Capacity that compounds — more from a leaner, stabler team
Effective capacity ↑
Team size — flat / leaner
productivity dividend
Jan 2027
Apr 2027
Oct 2027
Oct 2028
1. Ramp & stabilise (Jan 2027)
Onboarding and transition reach a steady baseline
2. AI-augmented delivery (Apr 2027)
Our own team's AI tooling lifts throughput per engineer — no estate footprint
3. Dialled AI (Oct 2027)
As you turn L1 dials, assisted flows raise platform-team throughput
4. Owned & optimised (Oct 2028)
Reusable patterns and a Pandora-owned CoE; capacity high, our footprint narrowing
More delivered, by a leaner and more stable team, an increasing share of it Pandora-owned — the opposite of bringing an army.

## Slide 14
13 THE DIAL
Three service levels, and the two gates between them
GATE 0 · foundations proven — estate-wide, passes once. Only then can any per-item dial move.
L0 · Run as-is
Conventional delivery, named solution, SLA-bound. The default — forever, if Pandora chooses.
G1
L1 · AI-assisted
AI drafts and recommends inside the existing process; a human executes every action. No new estate infrastructure; audit on. Unlocked per item by Gate 1 (after Gate 0).
G2
L2 · Agentic
The fabric owns a bounded loop behind approval gates. Unlocked per item by Gate 2 — never before a proven L1 track record.
Every item starts at L0 and stays there until you turn its dial. You hold all 30 dials.

## Slide 15
14 THE DIAL
The dial in action — the <30-minute workspace, same service three settings
Data-product workspace — the <30-minute story
Level 0 · from Jan 2027
Human-run · engineer approves & applies
Templated Terraform + Databricks via a ServiceNow request. Days become hours. A platform engineer still approves and applies.
Level 1 · earliest Apr–Oct 2027
AI-assisted · human approves every action
The request moves to Teams; Pandav assembles context from the graph, policy decides the route, a human approves — provisioning completes in under 30 minutes with an engineer touching only the approval. The RFP target lands here.
Level 2 · earliest Oct 2027+
Agent-run · human reviews outcomes
For pre-approved patterns within policy, provisioning runs automatically with outcome review. Only if the evidence says so, and only if you turn the dial.
Human (steel) → Agent (coral): the boundary slides right as the level rises — the human holds the gate until L2.

## Slide 16
15 THE DIAL
Everything you asked for — your goals, on the gentler path
12 of your 16 Data & Integration goals and 3 of 4 DevOps objectives are fully met at Level 0 — nothing agentic. Nothing needs Level 2. The dial governs pace, never coverage.
Ref | Your stated goal | Met at | Horizon
Data 01 | Data-product workspace < 30 min, no platform-engineer involv | Level 1 | Apr–Oct 2027
Data 02 | Near-real-time Nexus event data via Unity Catalog | Level 0 | Apr–Oct 2027
Data 03 | Discover / understand / trust via a single governance layer | Level 0 | Apr–Oct 2027
Data 04 | Centralized storage, open data format | Level 0 | Apr–Oct 2027
Data 05 | Rapidly productionize dashboards / pipelines (< 1 hour) | Level 1 | Apr–Oct 2027
Data 06 | Observe health & metrics; triage | Level 0 | Jan–Apr 2027
Data 07 | Granular cost transparency + proactive cost alarms | Level 0 | Apr 2027
Data 08 | Decommission EDW + Synapse; data-infra cost ~20% down | Level 0 | Oct 2027–Oct 2028
Integration 01 | Industry-leading standards — e2e automation, self-service | Level 1 | Apr–Oct 2027
Integration 02 | Reliable real-time + relaxed-latency data mart | Level 0 | Oct 2027
Integration 03 | AI-ready infrastructure | Level 0 | Apr–Oct 2027
Integration 04 | No data loss + end-to-end lifecycle transparency | Level 0 | Apr–Oct 2027
Integration 05 | Data-quality enforcement on Kafka | Level 0 | Apr–Oct 2027
Integration 06 | Flexible Kafka ingestion | Level 0 | Apr 2027
Integration 07 | Kong API developer portal + API standardization | Level 0 | Apr–Oct 2027
Integration 08 | Decommission BizTalk — while retaining operating competency | Level 0 | Strangler Oct 2027 · retired Oct 2028
DevOps 01 | Shared Kubernetes infrastructure — reduce duplication & over | Level 0 | Oct 2027–Oct 2028
DevOps 02 | Enable AI-assisted development tooling, incl. ADO→GitHub as | Level 1 | Jan–Apr 2027
DevOps 03 | End-to-end observability for business observability at scale | Level 0 | Apr–Oct 2027
DevOps 04 | DevEx & onboarding: golden paths, self-service, fast feedbac | Level 1 | Apr–Oct 2027

## Slide 17
16 THE JOURNEY
Re-anchored to the 30 Oct award — both lanes, four checkpoints
LANE 1 · RUN & DELIVER
LANE 2 · IMPROVE & EVOLVE
3 months · Jan 2027
Stabilise & assess
• Support-team transition complete (day 60, late Dec 2026): full on-call, P1/P2 owned • Dev-team transition in flight (days 60–120) • Baselines banked: DORA, developer NPS (16), cost, MTTx, ticket volumes
• Nothing in your estate — deliberately. • Our own delivery team uses AI internally (your approved tools, our machines). • Optional W1/W2 workshops draft the gate charter — a Pandora-owned artifact for later.
6 months · Apr 2027
Foundations proven
• Dev-team transition autonomous (day 120, Mar 2027); cutover on 50+ parameter evidence • A full quarter of SLAs proven at the RFP's numbers • Conventional automation wave 1: golden paths, dashboards, IaC
• If — and only if — Pandora turns the first dial: one Assist pilot in one item (e.g. access requests via Teams), 100% human-approved — through Gates 0 + 1 • AI dev-tooling enablement for Pandora engineers (your own stated goal)
12 months · Oct 2027
Selective dial-ups
• First cost-down banked; DORA trending up • Majority of one-time migrations done conventionally • BizTalk strangler underway on the plan and budget delivered in the first 90 days
• Assist broadened to dialled-up items only • First Delegate candidates where their Gate 2 passes • Agentic governance activates with the first estate touch — never before
24 months · Oct 2028
Earned scale
• Legacy retired: BizTalk, EDW, Synapse • All RFP targets met — at whichever level each item sits • Steady-state operations with a proven improvement cadence
• Items at whatever level Pandora chose — the fabric fully available, never mandatory • Same destination as the July approach. Arrival by consent.

## Slide 18
17 THE COST OF CAUTION
Shown, not hidden — what each target needs
RFP target | L0 | L1 | L2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
target | l0 | l1 | l2
Three headline targets — sub-30-min workspaces, minutes-onboarding, top-quartile DORA — are Level-1 outcomes. The dial is yours.

## Slide 19
18 WHY THIS IS LOW-RISK
Proven takeover · fabric already built · goals covered
Proven at Pandora
100 / 95 / 90 / 97
Our transition record in other Pandora product lines: 100% readiness criteria met, 95%+ documentation and runbooks generated, 90%+ tickets resolved independently in reverse shadow, 97%+ SLA achievement during stabilization.
Already built
0 R&D risk
The fabric is not a promise: Pandav runs on a standard container, the skill library is in production delivery use, the ops loop is designed. Keeping the option ready costs nothing.
Named coverage
30 / 30
Every scope row has a named conventional solution at Level 0. Coverage never depends on anything novel.
Goals covered
12/16 + 3/4
Your Data, Integration and DevOps platform goals fully met at Level 0; the remainder at Level 1 — one of which is your own AI-tooling goal. Nothing requires Level 2.

## Slide 20
19 WHAT WE NEED FROM PANDORA
Deliberately lighter — and how we start
WHAT WE NEED FROM PANDORA
• Transition access and environments — the RFP's own mobilisation needs, nothing more
• Named service owners per platform
• Monthly governance participation (the RFP's cadence)
• A quarterly dial review — 30 minutes inside the existing cadence
• Optional: the W1/W2 workshops to co-author the gate charter for later
• Not needed to start: any agentic decision, any new tooling in your estate, any process change for your teams
HOW WE START — FROM AWARD TO THE FIRST DIAL REVIEW
Week 0 · on award (30 Oct 2026)
Confirm transition start; mobilise Phase I support team per the RFP plan.
Weeks 1–6 · parallel, optional
W1 "Align — the map" and W2 "Define the gates": preparing the option, not committing to it. Every artifact Pandora-owned.
~Day 90 · Jan 2027
First quarterly dial review — the first moment any dial could turn, and equally the moment you can say "not yet" with zero consequence.

## Slide 21
20 · THE ASK
One decision starts the gentler path
THE ONE DECISION
Approve the alternative approach and confirm the transition start date. That is the whole ask.
WHAT STAYS YOURS
The dials, the gates, and the pace. Every dial-up needs your named owner's signature; every dial position is reviewed quarterly; "not yet" is always a valid answer.
WHAT STAYS READY
The agentic fabric — built, proven, and waiting behind Gate 0. The July approach remains available as the accelerated option whenever you want it.
Run as-is from day one. Build the foundations while we run. Earn every step toward agentic — at your pace, behind your gates, with your hand on the dial.